## Sheet 1
RFC Color
Change Owner Group | Start Date2 | Change# | Start Date | End Date | State | Short Description | Description | Requested By | Configuration Item | Change Impact | Downtime | Environments Impacted | Tasks | Assignment Group | Green | Red
Application IAM Group | 4/12/2026 | **CHG0129810** | 04/12/26 12:00 AM | 04/12/26 12:30 AM | Pending CAB Approval | Deploy ear file for UCTrustService, EPPNToOUD to IAM utility servers - Production (Changing LDAP connectivity to LDAPS ) | Environment: Production Deploy the EAR files for the two IAMUtilility applications - UCTrustService and EPPNToOUD to change LDAP connectivity to LDAPS (LDAP secure) connectivity | Gayathri Anand | UCTrust - Shibboleth SP - PROD | (Critical) (UCTrust - Shibboleth SP - PROD) UCTrustService and EPPNToOUD applications will be impacted. | 30 | Production | Application IAM Group (GAnand) | Application IAM Group
[13 empty] | Middleware Operations (KDay) | Middleware Operations
|  | **CHG0129812** | 04/12/26 12:00 AM | 04/12/26 12:30 AM | Pending CAB Approval | Prod - SimpleSAMLPHP upgrade from 2.4.2 to 2.4.4 | Upgrade SimpleSAMLPHP from 2.4.2 to 2.4.4 in Prod environment. sso-p-sml-x1 sso-p-sml-x2 sso-p-sml-x3 sso-p-sml-x4 | Gayathri Anand | SimpleSAMLphp - PROD | (Critical) (SimpleSAMLphp - PROD) users accessing SAML environment | 30 | Production | Application IAM Group (GAnand) | Application IAM Group
Database Administration Services | 4/11/2026 10:00:00 PM | **CHG0129926** | 04/11/26 10:00 PM | 04/12/26 06:00 AM | Pending CAB Approval | Monthly MS SQL prod patching | P-ITS-TESLDSQL1 P-ITS-TESSQL01 AYSO-P-SQL-W1 xerox-p-sql-w1 p-its-ccure01 ite-p-sql-w1 prcrmt-p-sql-w1 bigfix-p-sql-w1 casf-p-olps-w1 slogic-p-adm-w1 ite-p-sql-w3 ite-p-sql-w4 fm-p-dbc-w1 TES-P-SQL-W1 TES-L-SQL-W1 bfpa-d-sql-w1 | Vyacheslav Pankov | SQL Server | (Medium) (SQL Server) Bigfix, Ccure, PCS, AYSO, Procurement PTS, Loan, Xerox, TES, DBC | 30 | Production | Application IAM Group (MBoyce) | Application IAM Group
[13 empty] | AYSO (JKirton) | AYSO
[13 empty] | BASC (MRios) | BASC
[13 empty] | Database Administration Services (VPankov) | Database Administration Services
[13 empty] | Desktop Engineering (DYamamoto) | Desktop Engineering
[13 empty] | Infrastructure Application Support (LZeoli) | Infrastructure Application Support
[13 empty] | IT Asset (PAnderson) | IT Asset
[13 empty] | ITE (SMalani) | ITE
[13 empty] | Transcript Evaluation Service (VGuevara) | Transcript Evaluation Service
| 4/12/2026 | **CHG0129958** | 04/12/26 12:00 AM | 04/12/26 01:50 AM | Pending CAB Approval | Monthly MS SQL prod patching | P-ITS-RWDSQLR08 P-ITS-RWDSQLR09 P-ITS-RWDSQLR10 P-ITS-RWDSQLR03 | Rohit Kumar | SQL Server | (Critical) (SQL Server) Users will not be able to access the environments | 120 | Production | Database Administration Services (RKumar) | Database Administration Services
[13 empty] | Middleware Operations (SChen) | Middleware Operations
[13 empty] | Redwood Data Services (NMahadik) | Redwood Data Services
Infrastructure Operations | 4/15/2026 8:00:00 PM | **CHG0129934** | 04/15/26 08:00 PM | 04/16/26 06:00 AM | Pending Manager/CI Owner approval | Windows monthly patching - non-prod Windows servers | Apply Microsoft monthly security patches for non-prod Windows servers. Following is the link for the patch release. We are only patching security patches for Windows servers: https://technet.microsoft.com/en-us/library/security | Roong Uabhaibool | Server (Hardware) Windows | (High) (Server (Hardware) Windows) Minimal - monthly Microsoft monthly Security Patches | 15 |  | Database Administration Services () | Database Administration Services
[13 empty] | Infrastructure Operations (RUabhaibool) | Infrastructure Operations
[13 empty] | Middleware Operations () | Middleware Operations
[13 empty] | Reporting - Data Services () | Reporting - Data Services
| 4/16/2026 8:00:00 PM | **CHG0129936** | 04/16/26 08:00 PM | 04/17/26 06:00 AM | Pending Manager/CI Owner approval | Windows monthly patching - production Windows servers | Apply Microsoft monthly security patches for non-prod Windows servers. Following is the link for the patch release. We are only patching security patches for Windows servers: https://technet.microsoft.com/en-us/library/security | Roong Uabhaibool | Server (Hardware) Windows | (High) (Server (Hardware) Windows) Minimal - monthly Microsoft monthly Security Patches | 15 | Production | Infrastructure Operations (RUabhaibool) | Infrastructure Operations
[13 empty] | Reporting - Data Services (SVattikuti) | Reporting - Data Services
| 4/19/2026 12:01:00 AM | **CHG0129938** | 04/19/26 12:01 AM | 04/19/26 06:00 AM | Pending Manager/CI Owner approval | Windows monthly patching - Redwood production Windows servers | Apply Microsoft monthly security patches for Redwood prod Windows servers. Following is the link for the patch release. We are only patching security patches for Windows servers: https://technet.microsoft.com/en-us/library/security | Roong Uabhaibool | Server (Hardware) Windows | (Critical) (Server (Hardware) Windows) Minimal - monthly Microsoft monthly Security Patches | 15 | Production | Database Administration Services () | Database Administration Services
[13 empty] | Infrastructure Operations (RUabhaibool) | Infrastructure Operations
[13 empty] | Middleware Operations () | Middleware Operations
Middleware Operations | 4/12/2026 | **CHG0129758** | 04/12/26 12:00 AM | 04/12/26 01:30 AM | Pending CAB Approval | Middleware Patching - IAM-UTIL Servers - JBoss/Apache | The following Servers, Software, Versions and Target Versions are in scope for your application. iam-p-util-x1 iam-p-util-x2 JBOSS EAP: Current Version: JBOSS EAP 8.1.4 Target Version: JBOSS EAP 8.1.4-1 Apache JBSC: Current Version: Apache HTTP 2.4.62-9 Target Version: Apache HTTP 2.4.62-SP3 | Aman Dhingra | iam-p-util-x1.ucop.edu | (Critical) (iam-p-util-x1.ucop.edu) Services that use iam utility servers | 15 | Production | Application IAM Group (GAnand) | Application IAM Group
[13 empty] | Middleware Operations (ADhingra) | Middleware Operations
|  | **CHG0129760** | 04/12/26 12:00 AM | 04/12/26 06:00 AM | Pending CAB Approval | Middleware March 2026 Monthly Patching - Redwood ECM ICN Server | Redwood ECM Content Navigator (ICN) application has security related Middleware patching. The following Servers, Software, Versions and Target Versions are in scope. Servers: P-ITS-RWDFNCN01 ICN Applications: ICN Current Version: IBM Content Navigator 3.2.0 IF003 Target Version: IBM Content Navigator 3.2.0 IF004 | Aman Dhingra | REDWOOD-PROD_FN | (Critical) (REDWOOD-PROD_FN) Redwood ECM Users | 90 | Production | Database Administration Services () | Database Administration Services
[13 empty] | Infrastructure Operations (JLam) | Infrastructure Operations
[13 empty] | Middleware Operations (ADhingra) | Middleware Operations
|  | **CHG0129962** | 04/12/26 12:00 AM | 04/12/26 01:00 AM | Pending Manager/CI Owner approval | Middleware Monthly March Patching: SSO-P-IDP Servers | The following Servers, Software, Versions and Target Versions are in scope for your application. sso-p-idp-x3 sso-p-idp-x4 Current Version: Apache JBCS 2.4.62-9 Target Version: Apache JBCS 2.4.62-SP3 Current Version: Tomcat 10.1.36-8 Target Version: Tomcat 10.1.49-7 | Kit Day | iam-prod | (Critical) (iam-prod) Customers using the IDP PROD servers (including UCPath) | 15 | Production | Application IAM Group () | Application IAM Group
[13 empty] | Middleware Operations (KDay) | Middleware Operations
| 4/12/2026 12:01:00 AM | **CHG0129891** | 04/12/26 12:01 AM | 04/12/26 12:30 AM | Pending Manager/CI Owner approval | Identity and Access Management (Shibboleth): Middleware Monthly March Patching for SSO-P-SML servers | Hello, your SSO-P-SML application has security related Middleware updates being deployed this month. Please review the approved Middleware Patching Process document to understand flow and scope: https://ucofficeofthepresident.sharepoint.com/sites/its/itinfrastructure/cloud/SitePages/Middleware-Patching-Schedules.aspx The following Servers, Software, Versions and Target Versions are in scope for your application. sso-p-sml-x1 sso-p-sml-x2 sso-p-sml-x3 sso-p-sml-x4 Current Version: PHP 8.4.6.17 Target Version: PHP 8.5.4 Middleware Operations will backup existing versions before deploying new versions during the following Production standard change window. Sunday 04/12 12:01AM – 12:30AM Application Team must update this ServiceNow ticket 30 minutes before your scheduled window starts if you can't support this patch and would like to file a Security Exception. It will take approximately 1 hour to patch your middleware. Middleware Operations will update this ServiceNow ticket once completed. Application teams must validate functionality post patching and update this ServiceNow ticket if bugs are found. Requests to roll back the patch must be documented within this ticket. Requestor must also commit to filing a Security Exception to roll back a security patch. There will be one week to resolve any issues with patching conflicts before another ServiceNow ticket is assigned to patch the next environment. This process ends by either patching all middleware current in all environments, including production or when the Application Team files a Security Exception. Instructions for filing a Security Exception: https://ucofficeofthepresident.sharepoint.com/sites/InfoSec/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FInfoSec%2FShared%20Documents%2FSecurity%2DException%2DRequest%2D%2D%2DUser%2DProcedure%2Epdf&parent=%2Fsites%2FInfoSec%2FShared%20Documents | Carlos Aguillon | iam-prod | (High) (iam-prod) Auth services using SML SSO | 1 | Production | Application IAM Group () | Application IAM Group
[13 empty] | Middleware Operations (CAguillon) | Middleware Operations
| 4/12/2026 12:30:00 AM | **CHG0129759** | 04/12/26 12:30 AM | 04/12/26 01:30 AM | Pending CAB Approval | ERS: Middleware Monthly March 2026 Apache Patching | The following Servers, Software, Versions and Target Versions are in scope for your application. ERS-P-WEB-X1 ERS-P-WEB-X2 Apache: Current Version: Apache JBCS 2.4.62-9 Target Version: Apache JBCS 2.4.62-SP3 | Aman Dhingra | ERS - Effort Reporting System | (Critical) (ERS - Effort Reporting System) ERS users, downtime 30 minutes. | 0 | Production | Effort Reporting (KMeyyappan) | Effort Reporting
[13 empty] | Middleware Operations (ADhingra) | Middleware Operations
| 4/12/2026 8:00:00 AM | **CHG0129961** | 04/12/26 08:00 AM | 04/12/26 11:59 AM | Pending Manager/CI Owner approval | Redwood Prod Monthly Code Release New Framework - April 12th 2026 | Monthly Code Release to Redwood Production Environment *Redwood, Roots and UCRays users as the services will be down from Sunday, 04/12/26 08:00am- 11:59am | Aman Dhingra | Redwood/(PAS) Pension Administration System(AWS) | (Critical) (Redwood/(PAS) Pension Administration System(AWS)) Redwood, Roots and UCRays users as the services will be down from 8am-11am | 120 | Production | Database Administration Services (RKumar) | Database Administration Services
[13 empty] | Middleware Operations (CAguillon) | Middleware Operations
[13 empty] | Redwood-BIS (JMiller) | Redwood-BIS
[13 empty] | TDS Redwood Operational Support (CGuajardo) | TDS Redwood Operational Support
Network | 4/10/2026 11:20:15 AM | **CHG0129893** | 04/10/26 11:20 AM | 04/10/26 11:20 AM | Pending Manager/CI Owner approval | Upgrade Uplogix Control Center | The previous update did not apply the correct ciphers. This upgrade will correct that issue. | Scott Estes | Uplogix-PROD | (Low) (Uplogix-PROD) No customers are affected. This is a UCOP Network Team facing service and no other teams use it | 15 | Production | Network (SEstes) | Network
| 4/16/2026 7:00:00 AM | **CHG0129773** | 04/16/26 07:00 AM | 04/16/26 10:00 AM | Pending CAB Approval | Bring UP 2 HA tunnels to State Controllers Office from Global Protect Internal VPN | site 1 - riverside public peer 192.35.215.1 (FW IP for tunnel build) Private peer 128.48.110.98 (USER NAT) ! site 2 - Oakland public peer 192.12.86.2 (FW IP for tunnel build) Private peer 128.48.224.66 (USER NAT) ! CDT public peer 165.235.12.133 private peer 134.187.32.5 ! !phase1 crypto ikev2 proposal COMMON-ikev2-proposal encryption aes-gcm-256 prf sha256 group 14 86400 ! !phase2 crypto ipsec transform-set prodset8 esp-aes 256 esp-sha256-hmac PFS14 28800 mode tunnel ! crypto ikev2 keyring PEER-UCOPRIVERSIDE peer UCOPRIVERSIDE address 192.35.215.1 !yours inverse if needed permit ip host 134.187.32.5 host 128.48.110.98 ! crypto ikev2 keyring PEER-UCOPOAKLAND peer UCOPOAKLAND address 192.12.86.2 ! permit ip host 134.187.32.5 host 128.48.224.66 | Mikhail Gunn | Firewall | (Low) (Firewall) This does not impact any services or users as this is a new build | 0 | Production | Network (MGunn) | Network
PeopleSoft Support Services | 4/9/2026 8:00:00 PM | **CHG0129263** | 04/09/26 08:00 PM | 04/10/26 04:00 AM | Authorized - Approved\Scheduled | UCPATH SCI maintenance monthly - Non-production Maintenance (All non-prods) | Non-production Maintenance Date: April 9, 2026 Time: 8:00pm - 4:00am Pacific Remedy Ticket: REQ000002001619 Planned Activities: Patti provides Monthly: 1. All Appserver and messaging servers 2. All Pathlock Web and App servers ( FE) 3. All process schedulers 4. All CG domains o OS Patches • SFTP/FTP • Control M • GoldenGate • Fastpath • AMI • PUM Server • Linux o Terraform Library Change o Former Employee for UT1 cert change Notes: o UCPHRCP1 auto-refresh disabled during the maintenance window, refresh immediately following non-PRD maintenance. o App/Web/Prcs server reboots and cache cleared, IB domains bounced, standard maintenance activity. Instances impacted: 1. UCPHRDM2 2. UCPHRDEV 3. UCPHRTST 4. UCPHRCP1 5. UCPHRCP2 6. UCPHRUT1 8. UCPHRPJ1 9. UCPHRPJ2 10. UCPHRPJ3 11. UCPHRPJ4 12. UCPHRPJ5 13. UCPHRTR1 15. UCPRIDEV 16.UCPRIUT2 17. UCPRIPRD-RR | Long Dang | UCPath OS Patch - Non-PROD | (Critical) (UCPath OS Patch - Non-PROD) All UCPath non production | 360 | Test/ QA | Database Administration Services (RKumar) | Database Administration Services
[13 empty] | UCPath-PeopleSoft Admin (RSharma) | UCPath-PeopleSoft Admin
| 4/15/2026 | **CHG0129957** | 04/15/26 12:00 AM | 04/15/26 06:00 AM | Pending Manager/CI Owner approval | *SCI_Task* UCPath: Apply patch 38661558 to UCPHRTST | Why The Solution Will Resolve The Issue / What Will The Proposed Solution Do Patch 38661558 modifies PSPRPPS1.cbl so that, for retro transactions where retro is processing periods with a paygroup different from the current period and the transactions are not loaded to the paysheet, the process no longer updates the earnings begin and earnings end dates. Previously, those dates were still being updated for these transactions, which could incorrectly overwrite the earnings date values for the employee processed immediately before the current employee. | Rohit Doddavarapu | UCPHRTST | (High) (UCPHRTST) Ptest environment will not be available during the maintenance window being requested. | 60 | Test/ QA | Release Management (RGupta) | Release Management
[13 empty] | SCI AWS Cloud Ops (RDoddavarapu) | SCI AWS Cloud Ops
[13 empty] | UCPath-PeopleSoft Admin (MMarkee) | UCPath-PeopleSoft Admin
[13 empty] | UCPath-PeopleSoft Admin (RDoddavarapu) | UCPath-PeopleSoft Admin
| 5/3/2026 12:01:00 AM | **CHG0129910** | 05/03/26 12:01 AM | 05/03/26 06:00 AM | Pending Manager/CI Owner approval | *SCI_TASK* UCPHRPRD: Apply Tax Update 26-A [05/03/26 12:01:00 AM - 05/03/26 06:00:00 AM PST] | SCI will apply quarterly tax update 26-A to UCPHRPRD environment. | Martin Markee | UCPHRPRD | (Critical) (UCPHRPRD) UCPATH will have downtime while tax update is applied. | 360 | Production | SCI AWS Patching/Maintenance (MMarkee) | SCI AWS Patching/Maintenance
[13 empty] | UCPath-PeopleSoft Admin (MMarkee) | UCPath-PeopleSoft Admin
ServiceNow/ SMO | 4/9/2026 6:00:00 PM | CHG0129839 | 04/09/26 06:00 PM | 04/10/26 06:00 PM | Pending Manager/CI Owner approval | PCL Phase 2 : Decommission ServiceNow & Rapid7 integration, retire its associated processes/data as needed. | The existing Rapid7 integration will be decommissioned. As part of this effort, we will perform a ServiceNow platform cleanup to retire server records previously imported from InsightVM AWS scans. These records are now superseded by direct imports from AWS through the recently deployed ServiceNow SGC AWS Integration, and the Rapid7 data is no longer required for operational workflows or inventory management. There will be additional data clean up activities around migrating resources identified and classified as printers or other hardware resource types, if not already in the inventory, to their respective destination tables. Separately, InsightVM-driven classification has caused some non-server assets—printers and cameras—to land in server-class CMDB tables. That is incorrect for long-term inventory and reporting. This change supports the broader cleanup: retiring the Rapid7 path that feeds those mis-classifications, while a parallel effort migrates affected printer and camera records from server tables into the appropriate printer/hardware/CI tables and corrects discovery source and class as needed. Scope and sequencing for that migration will follow agreed data-owner rules and will not drop operational assets without validation. This change will remove all active connections and prevent any further data synchronization with Rapid7. No service impact is expected. | Sarah Mathews | ServiceNow - PROD | (Medium) (ServiceNow - PROD) No service impact is anticipated. Does not impact UCPath. | 0 | Production | ServiceNow/ SMO (KVallamsetla) | ServiceNow/ SMO
[13 empty] | ServiceNow/ SMO (SMathews) | ServiceNow/ SMO
TnT JIRA | 4/11/2026 9:00:00 AM | **CHG0129700** | 04/11/26 09:00 AM | 04/11/26 04:00 PM | Pending CAB Approval | archiving GL test cases for test repository cleanup project | As per TJSS ticket (https://ucopedu.atlassian.net/browse/TJSS-6820), we need to proceed with archiving the 1525 GL tests from the UCP prod space to the ARC prod space. The list of tests has been attached to this ticket as well as the Jira ticket. The suggested process is as follows but we will rely on what is right for Jira policy. Notification will be turned off temporarily during this change. | Andrew Hoffman | TnTJIRA-PROD | (Critical) (TnTJIRA-PROD) Jira is the only application impacted. There is no downtime, but notifications will be disabled for this period; all Jira users will be effected during this. | 0 | Production | TnT JIRA (AHoffman) | TnT JIRA
[13 empty] | TnT JIRA (JBeck) | TnT JIRA
UCPath-PeopleSoft Admin | 4/8/2026 7:00:00 PM | **CHG0129943** | 04/08/26 07:00 PM | 04/08/26 11:00 PM | Pending Manager/CI Owner approval | UCPath : Maintenance monthly release production | Production Maintenance - UCPHRPRD Date: Apr 08 , 2026. Time : 7:00 PM - 11:00 PM (Pacific) Remedy : TBD Planned activity: SCI team rolling bounce of App and web server UCPHRPRD for Post monthly release - CSR migration **There is No outage *** | Long Dang | UCPHRPRD | (Critical) (UCPHRPRD) UCPHRPRD | 0 | Production | SCI AWS Cloud Ops (LDang) | SCI AWS Cloud Ops
[13 empty] | UCPath Reporting Instance () | UCPath Reporting Instance
[13 empty] | UCPath-PeopleSoft Admin (RSharma) | UCPath-PeopleSoft Admin
| 4/19/2026 | **CHG0129668** | 04/19/26 12:00 AM | 04/19/26 06:00 AM | Pending CAB Approval | UCPath Pathlock A360 Implementation | Pathlock upgrade and A360 Implementation. | Rajeev Gupta | UCPHRPRD | (Low) (UCPHRPRD) No impact to UCPath as this activity is being done during normal maintenance window | 0 | Production | Release Management () | Release Management
[13 empty] | SCI AWS PSAdmin () | SCI AWS PSAdmin
[13 empty] | UCPath-PeopleSoft Admin () | UCPath-PeopleSoft Admin
| 4/30/2026 7:30:00 PM | **CHG0128357** | 04/30/26 07:30 PM | 04/30/26 11:30 PM | Pending Manager/CI Owner approval | UCPath : Maintenance monthly release production | Production Maintenance - UCPHRPRD Date: Apr. 30, 2026. Time : 7:30 PM - 11:30 PM (Pacific) Remedy : TBD Planned activity: SCI team rolling bounce of App and web server UCPHRPRD for Post monthly release - CSR migration **There is No outage *** ** CM team please add Gary additional approval** | Long Dang | UCPHRPRD | (Critical) (UCPHRPRD) UCPHRPRD | 0 | Production | SCI AWS Cloud Ops (LDang) | SCI AWS Cloud Ops
[13 empty] | UCPath Reporting Instance () | UCPath Reporting Instance
[13 empty] | UCPath-PeopleSoft Admin (RSharma) | UCPath-PeopleSoft Admin